## Summary
CEM Production Deployment
Date:
Scheduled Time | 5/28/2020 08.30:00 AM - 5/28/2020 09.30:00 AM
Communication Bridge | WebEx: TBD
CR # | 27149
Brands | PLUS
Deployment Manager | Rittika Jindal
Deployment Facilitator | Rittika Jindal & Pradosh Kumar Jena
Playbook Final Approval Date

## gcpinteg
GCP
Steps will be run in number order. Steps with the same number will/can be executed simultaniously. | [7 empty] | Overall Task Completion
Deployment Activities
# | Activity | Subject Area | Resource | Proposed Start time (ET) | Duration (Mins) | Proposed End Time (ET) | % Complete | Actual Start Time (ET) | Actual End Time (ET) | Remarks
Code Deployment
Deployment of changes for mart email table for Plus
| cp /home/svc_gcpintegnp/util/plus/cp_crm_email_mart.bq ~/util/plus/ | Reset Mart Table | Pradosh Kumar Jena | 5/28/2020 08.30:00 AM |  | 5/28/2020 09.30:00 AM | Done
| execute /home/gcpinteg/util/plus/cp_crm_email_mart.bq | Reset Mart Table | Pradosh Kumar Jena | 5/28/2020 08.30:00 AM |  | 5/28/2020 09.30:00 AM | Done
| cp /home/svc_gcpintegnp/script/plus_brand_customer_email.bq ~/script | CRM Mart Table | Pradosh Kumar Jena | 5/28/2020 08.30:00 AM |  | 5/28/2020 09.30:00 AM | Done
| execute run_bq_job -e plus_brand_customer_email.bq | CRM Mart Table | Pradosh Kumar Jena | 5/28/2020 08.30:00 AM |  | 5/28/2020 09.30:00 AM | Done

## ascgcpinteg_p
GCP
Steps will be run in number order. Steps with the same number will/can be executed simultaniously. | [7 empty] | Overall Task Completion
Deployment Activities
# | Activity | Subject Area | Resource | Proposed Start time (ET) | Duration (Mins) | Proposed End Time (ET) | % Complete | Actual Start Time (ET) | Actual End Time (ET) | Remarks
Configuration Change

## svc_gcpintegnp
GCP
Steps will be run in number order. Steps with the same number will/can be executed simultaniously. | [7 empty] | Overall Task Completion
Deployment Activities
# | Activity | Subject Area | Resource | Proposed Start time (ET) | Duration (Mins) | Proposed End Time (ET) | % Complete | Actual Start Time (ET) | Actual End Time (ET) | Remarks
Configuration Change

## Issues
Deployment issues
SL # | Brand | Component | Issue | Comments | Status | Reported By | Deployment | Time Taken to Resolve
QA validation issues
SL # | Brand | Component | Issue | Comments | JIRA# | Status
1