## Summary
CEM Production Deployment
Date:
Scheduled Time | 4/16/2020 4:00 PM - 4/17/2020 8:00 AM
Communication Bridge | WebEx: TBD
CR # | TBD
Brands | PLUS/PRE
Deployment Manager | Christian Snediker-Morscheck
Deployment Facilitator | Christian Snediker-Morscheck, Rittika Jindal & Ghiridhar Velu
Playbook Final Approval Date | 2020-04-13

## gcpinteg
GCP
Steps will be run in number order. Steps with the same number will/can be executed simultaniously. | [7 empty] | Overall Task Completion
Deployment Activities
# | Activity | Subject Area | Resource | Proposed Start time (ET) | Duration (Mins) | Proposed End Time (ET) | % Complete | Actual Start Time (ET) | Actual End Time (ET) | Remarks
Configuration Change
1 | crontab -e; #shutdown bq job service | Pre deployment set up | CSM | 16:30 | 1
2 | Lockdown gcpinteg | Pre deployment set up | CSM | 16:31 | 1 |  |  |  |  | lock down prod
3 | Use gcloud to change default project to p-ascn-da-aadp-001 | Pre deployment set up | CSM | 16:32 | 10 |  |  |  |  | aadp-001 project becomes production
4 | Update set_env.sh - switch prod & nonprod env | Pre deployment set up | CSM | 16:42 | 5 |  |  |  |  | Source script and validate confirm default bucket
Code Deployment (util)
5 | bckp_analytic_mart.bq | Implementation scripts | CSM | 16:45 |  | 17:00
5 | bckp_conform.bq | Implementation scripts | CSM | 16:45 |  | 17:00
5 | bckp_stage.bq | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/fndtn/cp_stage.bq | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/fndtn/cp_conform.bq | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/fndtn/cp_analytic_mart.bq | Implementation scripts | CSM | 16:45 |  | 17:00
5 | upgrade_bq_job_status.bq | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/pre/reset_buckets | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/pre/fix_stage.sh | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/pre/go_qa_stage.sh | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/pre/rebuild_views | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/pre/fix_pre_mart.sh | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/plus/reset_buckets | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/plus/build_stage.sh | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/plus/go_qa_stage.sh | Implementation scripts | CSM | 16:45 |  | 17:00
5 | util/plus/fix_plus_mart.sh | Implementation scripts | CSM | 16:45 |  | 17:00
Code Deployment (lib&bin)
5 | common.sh | lib scripts | CSM | 16:45 |  | 17:00
5 | set_env.sh | lib scripts | CSM | 16:45 |  | 17:00
5 | run_bq_job | bin | CSM | 16:45 |  | 17:00
5 | gsload | bin | CSM | 16:45 |  | 17:00
Code Deployment (schema)
5 | schema/edl_landing/*.json | table schema | CSM | 16:45 |  | 17:00
5 | schema/edl_stage/*.json | table schema | CSM | 16:45 |  | 17:00
Code Deployment (script)
5 | plus_edw.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | plus_crm.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | plus_mart_daily_load.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | plus_store.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | pre_atg.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | pre_aw.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | pre_bi.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | pre_dom.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | pre_mart_load.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | pre_sapd.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | pre_sapwm.sh | shell scripts | CSM | 16:45 |  | 17:00
5 | ann_atg_returns.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_atg_transactions.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_aw_transactions_discountdtl.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_aw_transactions_header.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_aw_transactions_line.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_aw_transactions_linenotes.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_aw_transactions_merchdtl.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_aw_transactions_returndtl.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_aw_transactions_taxdetail.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_bi_transaction_fpnfp.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_dom_bopis_transactions.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_sap_exchrate.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_sap_product.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_sap_store.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_sap_style.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_sap_vendor_bkp.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_sap_vendor.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | ann_sap_vendor_new.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | dim_brand_customer.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | dim_item.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | dim_item_hist.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | dim_store.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | dim_store_hist.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction_detail.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction_discount.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction_fee.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction_merch_line.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction_notes.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction_tax.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | fact_transaction_tender.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | lbca_sales_transaction_detail_bkp19.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | lbca_sales_transaction_detail_bkp.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | lbca_sample.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | lbca_sku_attr_channel_bkp17.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | lb_sales_transaction_detail.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | lb_sales_transaction_discount.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | lb_store.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_item_sku.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_mart_transaction_notes.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_customer.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_detail.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_discount.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_fee.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_header.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_notes.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_payment.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_tax.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sales_transaction_tender.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_sku_attr_channel.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_store.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_tmci997_esp_outbound.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci015_cust_ccard.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci016_ccard_type.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci019_customer.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci019_custonly.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci021_cust_phone.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci067_cust_block.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci079_club_memb.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci105_chain_cust.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci172_chain_cust_email.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci173_full_email_address.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci173_full_email_addr_status.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci180_cust_demog.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci396_curr_opt_in_out_full.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci972_chain_cust_fullemail.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | plus_vmci995_esp_last_click_open.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_commerceitemadjustments.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_commerceitem.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_commerceitemcoupons.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_header.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_payment.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_return.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_return_commerceitem.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_return_method.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_shipment.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_atg_order_shipment_tracking.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_class.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_item.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_sap_promo.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_store.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_style.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_transaction_header.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | pre_transaction_item.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | transaction_customer_xref.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | vmci019_custonly.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | vmci021_cust_phone.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | vmci172_chain_cust_email.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | vmci173_full_email_address.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | vmci173_full_email_addr_status.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | vmci180_cust_demog.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | vmci396_curr_opt_in_out_full.bq | bq scripts | CSM | 16:45 |  | 17:00
5 | val/ann_ann_aw_transactions_taxdetail-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/ann_ann_sap_exchrate-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/ann_ann_sap_product-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/ann_sap_store-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/ann_sap_vendor-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_item_sku-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_customer-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_detail-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_discount-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_fee-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_header-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_notes-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_payment-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_tax-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sales_transaction_tender-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_sku_attr_channel-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_store-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_tmci997_esp_outbound-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci015_cust_ccard-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci016_ccard_type-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci019_customer-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci019_custonly-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci021_cust_phone-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci067_cust_block-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci079_club_memb-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci105_chain_cust-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci172_chain_cust_email-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci173_full_email_address-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci173_full_email_addr_status-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci180_cust_demog-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci396_curr_opt_in_out_full-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci396_curr_opt_in_out_full-Validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci972_chain_cust_fullemail-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/plus_vmci995_esp_last_click_open-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/pre_atg_order_commerceitemadjustments-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/pre_atg_order_commerceitemcoupons-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/pre_atg_order_commerceitem-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/pre_atg_order_payment-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/pre_atg_order_shipment_tracking-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
5 | val/pre_atg_order_shipment-validation.bq | validation scripts | CSM | 16:45 |  | 17:00
IDL Execution
6 | bckp_analytic_mart.bq | foundation idl | CSM | 17:01 |  | 17:05
6 | bckp_conform.bq | foundation idl | CSM | 17:01 |  | 17:05
6 | bckp_stage.bq | foundation idl | CSM | 17:01 |  | 17:05
7 | execute util/fndtn/cp_stage.bq | foundation idl | CSM | 17:06 |  | 17:07
8 | execute util/fndtn/cp_conform.bq | foundation idl | CSM | 17:08 |  | 17:09
9 | execute util/fndtn/cp_analytic_mart.bq | foundation idl | CSM | 17:10 |  | 17:11
10 | execute util/pre/reset_buckets | pre idl | CSM | 21:30 |  | 21:33 |  |  |  | Will load buckets, starting with April fw1
11 | execute util/pre/fix_stage.sh | pre idl | CSM | 21:34 |  | 21:44
12 | execute util/pre/go_qa_stage.sh | pre idl | CSM | 21:45 |  | 21:45 |  |  |  | Verify /data/ctl control files before next step
14 | execute run_bq_job | pre idl | CSM | 22:16 |  | 22:25
15 | execute util/pre/rebuild_views | pre idl | CSM | 22:26 |  | 22:26
16 | execute util/pre/fix_pre_mart.sh | pre idl | CSM | 22:27 |  | 22:30
17 | execute script/pre_mart_load.sh | pre idl | CSM | 22:31 |  | 22:31 |  |  |  | Verify /data/ctl control files before next step
*** plus execute steps ***
10 | execute util/plus/reset_buckets | plus idl | RJ | 21:30 |  | 21:33
11 | util/plus/plus_build_stage.bq | plus idl | RJ | 21:34 |  | 21:44
12 | execute util/plus/go_qa_stage.sh | plus idl | RJ | 21:45 |  | 21:45 |  |  |  | Verify /data/ctl control files before next step
13 | execute run_bq_job | pre idl | RJ | 21:46 |  | 22:15 |  |  |  | Verify /data/ctl control files for ATG tables before next step
15 | execute util/plus/fix_plus_mart.sh | plus idl | RJ | 22:16 |  | 22:25
17 | execute script/plus_mart_load.sh | plus idl | RJ | 22:26 |  | 22:26
18 | execute run_bq_job | pre idl | RJ | 22:32 |  | 22:45
QA High Level Sanity / Detail Sanity
19 | Review status table |  |  | 22:45 |  | 23:00
Post Deployment : Operational Activities
20 | crontab -e; #restart bq job service |  | Christian | 23:00
21 | Release mart control-m jobs from hold |  | Giri will validate | 8:00
Post Deployment : Final Validation

## ascgcpinteg_p
GCP
Steps will be run in number order. Steps with the same number will/can be executed simultaniously. | [7 empty] | Overall Task Completion
Deployment Activities
# | Activity | Subject Area | Resource | Proposed Start time (ET) | Duration (Mins) | Proposed End Time (ET) | % Complete | Actual Start Time (ET) | Actual End Time (ET) | Remarks
Configuration Change
1 | crontab -l > schedule_bkup.cron | Pre deployment set up | CSM | 16:00 | 1 |  |  |  |  | Backup EDL to GCP schedule
2 | crontab -e | Pre deployment set up | CSM | 16:01 | 1 |  |  |  |  | Backup EDL to GCP schedule

## svc_gcpintegnp
GCP
Steps will be run in number order. Steps with the same number will/can be executed simultaniously. | [7 empty] | Overall Task Completion
Deployment Activities
# | Activity | Subject Area | Resource | Proposed Start time (ET) | Duration (Mins) | Proposed End Time (ET) | % Complete | Actual Start Time (ET) | Actual End Time (ET) | Remarks
Configuration Change
2 | Lockdown svc_gcpintegnp | Pre deployment set up | CSM | 16:31 | [5 empty] | lock down prod
3 | Use gcloud to change default project to p-asna-analytics-002 | Pre deployment set up | CSM | 16:32 | [5 empty] | aadp-001 project becomes production
3 | Verify default bucket is in p-asna-analytics-002 | Pre deployment set up | CSM | 16:33

## Issues
Deployment issues
SL # | Brand | Component | Issue | Comments | Status | Reported By | Deployment | Time Taken to Resolve
QA validation issues
SL # | Brand | Component | Issue | Comments | JIRA# | Status
1