## Sheet1
S.No | Task | Owner | Start Time(EST) | End Time(EST) | Status | Comments
1 | Incremental Load for 04/02 | CDP Team | 21:25 PM | 0:58 | Completed
2 | ATG Registered Customer Feed | CDP Team | 1:30 | 1:58 | Completed
3 | ATG Guest Customer/ ORPOS IBR Feed | CDP Team | 3:05 | 3:53 | Completed
4 | CRM History Incremental Extract | CRM Team | 0:25 | 2:50 | Completed | Includes 9 history incremental feeds, merge and customer activity
5 | Load customer activity in raw layer | CDP Team | 2:40 | 2:58 | Completed | Customer activity to be loaded as soon as CRM provides the extract
6 | History Incremental - CRON JOB 1 - Initiation | CDP Team | 2:30 | 2:35 | Completed | This is automated execution, team to monitor progress of each job and call out issues if any immediately
7 | History Incremental - CRON JOB 2 - Decrypt | CDP Team | 2:40 | 2:40 | Completed
8 | History Incremental - CRON JOB 3 - RawLayer Load | CDP Team | 2:45 | 2:50 | Completed
9 | History Incremental - CRON JOB 4 - Conform Layer Load | CDP Team | 9:02 | 11:44 | Completed
10 | legacy customer ID feed Extraction from Teradata | CDP Team | 1:10 | 1:32 | Completed | Do when no TPT job is running in CRM end.
(ORPOS, ECOM, EMP and PLCC)
11 | Legacy Customer ID Update | CDP Team | 2:15 | 2:35 | Completed
(ORPOS, ECOM, EMP and PLCC)
12 | Merge | CDP Team | 11:44 | 13:02 | Completed | Use the command line provided in email for Merge. Merge script will also trigger legacy customer id update queries.
13 | Transaction Incremental - Conform Layer | CDP Team | 3:16 | 4:55 | Completed | This activity is independent and should be done in parallel with task 6. Make sure we run the script as .q and not as separate queries.
Tables for transaction incremental to be prepared before 3:00 est.
14 | Transaction Incremental - Campaign Mart | CDP Team | 4:55 | 5:09 | Completed | Inform Unica team as soon as transaction campaign mart is loaded. This activity is dependent only on task #13
15 | Persona transaction xref | CDP Team | 13:02 | 14:21 | Completed | Trigger this once task 12 is complete.
16 | click open and soft bounce and Real_time_396 | CDP Team | 14:21 | 16:04 | Completed | Trigger this once task 15 is complete
17 | LOYL_Persona_Creation | CDP Team | 16:11 | 16:19 | Completed
18 | store & item incremental | CDP Team |  |  | Completed | Run before Brand_Customer - Conform_Layer and after XREF
19 | Brand Customer - Conform Layer | CDP Team | 16:41 |  | In progress | After running campaign store and campaign item
PLUS Loyalty Batch Status
| CA Transaction Header |  |  |  |  | Loyalty Feed source is switched to Sales Audit on 03/31 and these batches disabled in EDL system on 04/02.
CA Transaction Detail
CA Certificate
CA Transaction Header Report
CA Transaction Detail Report
LB Transaction Header
LB Transaction Detail
LB Certificate
LB Transaction Header Report
LB Transaction Detail Report
| Loyalty Lane Bryant Account Update | CDP Team | 11:00 | 11:19 AM | Completed
| Loyalty Lane Bryant CRM Account Update | CDP Team | 11:18 | 11:19 | Completed
| Loyalty Lane Bryant Account Update Report | CDP Team | 11:17 | 11:18 | Completed | Dependent on LB Account Update successful completion
| Loyalty Catherine’s Account Update | CDP Team | 11:30 | 11:46 AM | Completed
| Loyalty Catherine’s CRM Account Update | CDP Team | 11:45 | 11:46 | Completed
| Loyalty Catherine’s Account Update Report | CDP Team | 11:44 | 11:45 | Completed | Dependent on CA Account Update successful completion